## Cont Acquisition Schedule
|  | Julian Required On Site (ROS) Date | McMurdo- Calendar Required On Site (ROS) Date | South Pole- Calendar Required On Site (ROS) Date | Maximo Purchase Request Submittal Deadline | Required Delivery Date To PT Hueneme | NOTES
Start of MCM Heavy Airlift | CONTINENTAL OR CONUS, NO POLE | 1282 | 2021-10-09 | N/A | 2021-07-07 | 2021-08-07 | 1
| CONTINENTAL OR CONUS, NO POLE | 1289 | 2021-10-16 | N/A | 2021-07-14 | 2021-08-14 | 1
| CONTINENTAL OR CONUS, NO POLE | 1296 | 2021-10-23 | N/A | 2021-07-21 | 2021-08-21 | 1
| CONTINENTAL OR CONUS, NO POLE | 1303 | 2021-10-30 | N/A | 2021-07-28 | 2021-08-28 | 1
South Pole/Field Sites open | CONTINENTAL OR CONUS | 1310 | 2021-11-06 | 2021-11-06 | 2021-08-04 | 2021-09-04 | 2,3
Heavy Airlift Gap Period | CONTINENTAL OR CONUS | 1317 | 2021-11-13 | 2021-11-13 | 2021-08-11 | 2021-09-11 | 2,3
| CONTINENTAL OR CONUS | 1324 | 2021-11-20 | 2021-11-20 | 2021-08-18 | 2021-09-18 | 2,3
| CONTINENTAL OR CONUS | 1331 | 2021-11-27 | 2021-11-27 | 2021-08-25 | 2021-09-25 | 2,3
| CONTINENTAL OR CONUS | 1338 | 2021-12-04 | 2021-12-04 | 2021-09-01 | 2021-10-02 | 2,3
| CONTINENTAL OR CONUS | 1345 | 2021-12-11 | 2021-12-11 | 2021-09-08 | 2021-10-09 | 2.3
| CONTINENTAL OR CONUS | 1352 | 2021-12-18 | 2021-12-18 | 2021-09-15 | 2021-10-16 | 2,3
AIRLIFT BLACKOUT PERIOD <<<<<NO SCHEDULED USAP AIRLIFT IN THIS PERIOD>>>>> | CONUS ONLY- AIRLIFT GAP | 1359 | N/A | N/A | 2021-10-27 | 2021-12-08 | 4
| CONUS ONLY- AIRLIFT GAP | 2001 | N/A | N/A | 2021-11-03 | 2021-12-15 | 4
| CONUS ONLY- AIRLIFT GAP | 2008 | N/A | N/A | 2021-11-10 | 2021-12-22 | 4
| CONUS ONLY- AIRLIFT GAP | 2015 | N/A | N/A | 2021-11-17 | 2021-12-29 | 4
| CONUS ONLY- AIRLIFT GAP | 2022 | N/A | N/A | 2021-11-24 | 2022-01-05 | 4
| CONTINENTAL OR CONUS | 2029 | 2022-01-29 | 2022-01-29 | 2021-10-27 | 2021-11-27 | 2,3
| CONTINENTAL OR CONUS | 2036 | 2022-02-05 | 2022-02-05 | 2021-11-03 | 2021-12-04 | 2,3
Start of South Pole winter | CONTINENTAL OR CONUS | 2043 | 2022-02-12 | 2022-02-12 | 2021-11-10 | 2021-12-11 | 2
| CONTINENTAL OR CONUS, NO POLE | 2050 | 2022-02-19 | N/A | 2021-11-17 | 2021-12-18 | 1
Final Summer airlift to McMurdo | CONTINENTAL OR CONUS, NO POLE | 2057 | 2022-02-26 | N/A | 2021-11-24 | 2022-12-25 | 1
McMurdo winter flight #1 | CONTINENTAL OR CONUS, NO POLE | 2232 | 2022-08-20 | N/A | 2022-05-18 | 2022-06-18 | 1
Resupply Vessel |  | Julian Required On Site (ROS) Date | McMurdo- Calendar Required On Site (ROS) Date | South Pole- Calendar Required On Site (ROS) Date | Maximo Purchase Request Submittal Deadline | Required Delivery Date To PT Hueneme
MCM/SP - VESSEL- TIER 1- LIFE/HEALTH/SAFETY |  | 2121 | 2022-01-29 | 2022-02-12 | 2021-10-24 | 2021-12-05 | 5
MCM/SP - VESSEL- TIER 2- CRITICAL |  | 2122 | 2022-01-29 | 2022-02-12 | 2021-10-24 | 2021-12-05 | 5
MCM/SP - VESSEL - TIER 3- ESSENTIAL |  | 2123 | 2022-01-29 | 2022-02-12 | 2021-10-24 | 2021-12-05 | 5
MCM/SP - VESSEL - NON-TIERED RESUPPLY |  | 2124 | 2022-01-29 | 2023-11-01 | 2021-10-24 | 2021-12-05 | 5,6
1 | These ROS dates are open only for McMurdo Station materials, there is no airlift to South Pole or deep fleild sites available
2 | These ROS dates are open for South Pole materials
3 | These ROS dates are open for deep field camp materials
4 | There is no available airlift between Christchurch, NZ and McMurdo
5 | Resupply vessel arrival dates to McMurdo are notional and are subject to change. Resupply vessel dates are structured to indicate tiered priority of inbound materials
6 | ROS 2124 should be selected for non-tiered cargo for McMurdo and South Pole materials which will over-winter for usage the following FY